## CompleteParse
Knowledge Area | Process Group | Process | Attribute | Value
Initiating | Integration | Develop Project Charter | Inputs | SOW
Initiating | Integration | Develop Project Charter | Inputs | Business Case
Initiating | Integration | Develop Project Charter | Inputs | Agreements
Initiating | Integration | Develop Project Charter | Inputs | Enterprise Environmental Factors
Initiating | Integration | Develop Project Charter | Inputs | Organization Process Assets
Initiating | Integration | Develop Project Charter | Tools/Tech's | Expert Judgement
Initiating | Integration | Develop Project Charter | Tools/Tech's | Facilitation Techniques
Initiating | Integration | Develop Project Charter | Outputs | Project Charter
Planning | Integration | Develop Project Management Plan | Inputs | Project Charter
Planning | Integration | Develop Project Management Plan | Inputs | Outputs from other processes
Planning | Integration | Develop Project Management Plan | Inputs | Enterprise Environmental Factors
Planning | Integration | Develop Project Management Plan | Inputs | Organization Process Assets
Planning | Integration | Develop Project Management Plan | Tools/Tech's | Expert Judgement
Planning | Integration | Develop Project Management Plan | Tools/Tech's | Facilitation Techniques
Planning | Integration | Develop Project Management Plan | Outputs | Project Management Plan
Executing | Integration | Direct and Manage Project | Inputs | Project Mgt Plan
Executing | Integration | Direct and Manage Project | Inputs | Approved Change Requests
Executing | Integration | Direct and Manage Project | Inputs | Enterprise Environmental Factors
Executing | Integration | Direct and Manage Project | Inputs | Organization Process Assets
Executing | Integration | Direct and Manage Project | Tools/Tech's | Expert Judgement
Executing | Integration | Direct and Manage Project | Tools/Tech's | PM Information Systems
Executing | Integration | Direct and Manage Project | Tools/Tech's | Meetings
Executing | Integration | Direct and Manage Project | Outputs | Deliverables
Executing | Integration | Direct and Manage Project | Outputs | Work Performance Data
Executing | Integration | Direct and Manage Project | Outputs | Change Requests
Executing | Integration | Direct and Manage Project | Outputs | PM Plan Updates
Executing | Integration | Direct and Manage Project | Outputs | Project Doc Updates
Monitoring/Controlling | Integration | Monitor and Control Project Work | Inputs | Project Mgt Plan
Monitoring/Controlling | Integration | Monitor and Control Project Work | Inputs | Sked Forecasts
Monitoring/Controlling | Integration | Monitor and Control Project Work | Inputs | Cost Forecasts
Monitoring/Controlling | Integration | Monitor and Control Project Work | Inputs | Validated Changes
Monitoring/Controlling | Integration | Monitor and Control Project Work | Inputs | Work Performance Information
Monitoring/Controlling | Integration | Monitor and Control Project Work | Inputs | Enterprise Environmental Factors
Monitoring/Controlling | Integration | Monitor and Control Project Work | Inputs | Organization Process Assets
Monitoring/Controlling | Integration | Monitor and Control Project Work | Tools/Tech's | Expert Judgement
Monitoring/Controlling | Integration | Monitor and Control Project Work | Tools/Tech's | PM Information Systems
Monitoring/Controlling | Integration | Monitor and Control Project Work | Tools/Tech's | Meetings
Monitoring/Controlling | Integration | Monitor and Control Project Work | Outputs | Deliverables
Monitoring/Controlling | Integration | Monitor and Control Project Work | Outputs | Work Performance Data
Monitoring/Controlling | Integration | Monitor and Control Project Work | Outputs | Change Requests
Monitoring/Controlling | Integration | Monitor and Control Project Work | Outputs | PM Plan Updates
Monitoring/Controlling | Integration | Monitor and Control Project Work | Outputs | Project Doc Updates
Monitoring/Controlling | Integration | Perform Integrated Change Control | Inputs | Project Mgt Plan
Monitoring/Controlling | Integration | Perform Integrated Change Control | Inputs | Work Performance Reports
Monitoring/Controlling | Integration | Perform Integrated Change Control | Inputs | Change Requests
Monitoring/Controlling | Integration | Perform Integrated Change Control | Inputs | Enterprise Env. Factors
Monitoring/Controlling | Integration | Perform Integrated Change Control | Inputs | Org. Process Assets
Monitoring/Controlling | Integration | Perform Integrated Change Control | Tools/Tech's | Expert Judgement
Monitoring/Controlling | Integration | Perform Integrated Change Control | Tools/Tech's | Meetings
Monitoring/Controlling | Integration | Perform Integrated Change Control | Tools/Tech's | Change Control Tools
Monitoring/Controlling | Integration | Perform Integrated Change Control | Outputs | Approved Change Requests
Monitoring/Controlling | Integration | Perform Integrated Change Control | Outputs | Change Log
Monitoring/Controlling | Integration | Perform Integrated Change Control | Outputs | PM Plan Updates
Monitoring/Controlling | Integration | Perform Integrated Change Control | Outputs | Project Doc Updates
Closing | Integration | Close Project | Inputs | Project Mgt Plan
Closing | Integration | Close Project | Inputs | Accepted Deliverables
Closing | Integration | Close Project | Inputs | Org. Process Assets
Closing | Integration | Close Project | Tools/Tech's | Expert Judgement
Closing | Integration | Close Project | Tools/Tech's | Analytical Techniques (regression and trend analysis)
Closing | Integration | Close Project | Tools/Tech's | Meetings
Closing | Integration | Close Project | Outputs | Final Product
Closing | Integration | Close Project | Outputs | Service or Result Transition
Closing | Integration | Close Project | Outputs | Organizational Process Updates
Planning | Scope | Plan Scope Management | Inputs | Project Mgt Plan
Planning | Scope | Plan Scope Management | Inputs | Project Charter
Planning | Scope | Plan Scope Management | Inputs | Enterprise Environmental factors
Planning | Scope | Plan Scope Management | Inputs | Org. Process Assets
Planning | Scope | Plan Scope Management | Tools/Tech's | Expert Judgement
Planning | Scope | Plan Scope Management | Tools/Tech's | Meetings
Planning | Scope | Plan Scope Management | Outputs | Scope Management Plan
Planning | Scope | Plan Scope Management | Outputs | Requirements Management Plan
Planning | Scope | Collect Requirements | Inputs | Scope Mgmt Plan
Planning | Scope | Collect Requirements | Inputs | Requirements Mgmt Plan
Planning | Scope | Collect Requirements | Inputs | Stakeholder Mgmt Plan
Planning | Scope | Collect Requirements | Inputs | Project Charter
Planning | Scope | Collect Requirements | Inputs | Stakeholder Register
Planning | Scope | Collect Requirements | Tools/Tech's | Interviews
Planning | Scope | Collect Requirements | Tools/Tech's | Focus Groups
Planning | Scope | Collect Requirements | Tools/Tech's | Facilitated Workshops
Planning | Scope | Collect Requirements | Tools/Tech's | Group Creativity
Planning | Scope | Collect Requirements | Tools/Tech's | Group Decision Making
Planning | Scope | Collect Requirements | Tools/Tech's | Questionaires & Surveys
Planning | Scope | Collect Requirements | Tools/Tech's | Observations
Planning | Scope | Collect Requirements | Tools/Tech's | Prototypes
Planning | Scope | Collect Requirements | Tools/Tech's | Benchmarking
Planning | Scope | Collect Requirements | Tools/Tech's | Context Diagrams
Planning | Scope | Collect Requirements | Tools/Tech's | Document Analysis
Planning | Scope | Collect Requirements | Outputs | Requirements Documentation
Planning | Scope | Collect Requirements | Outputs | Requirements Traceability Matrix
Planning | Scope | Define Scope | Inputs | Scope Management Plan
Planning | Scope | Define Scope | Inputs | Project Charter
Planning | Scope | Define Scope | Inputs | Requirements Documentation
Planning | Scope | Define Scope | Inputs | Org. Process Assets
Planning | Scope | Define Scope | Tools/Tech's | Expert Judgement
Planning | Scope | Define Scope | Tools/Tech's | Product Analysis
Planning | Scope | Define Scope | Tools/Tech's | Alternatives Generation
Planning | Scope | Define Scope | Tools/Tech's | Facilitated Workshops
Planning | Scope | Define Scope | Outputs | Project Scope Statement
Planning | Scope | Define Scope | Outputs | Project Documents Updates
Planning | Scope | Create WBS | Inputs | Scope Mgmt Plan
Planning | Scope | Create WBS | Inputs | Proj Scope Statement
Planning | Scope | Create WBS | Inputs | Requirements Docs
Planning | Scope | Create WBS | Inputs | Enterprise Enviro Factors
Planning | Scope | Create WBS | Inputs | Org. Process Assets
Planning | Scope | Create WBS | Tools/Tech's | Decomposition
Planning | Scope | Create WBS | Tools/Tech's | Expert Judgement
Planning | Scope | Create WBS | Outputs | Scope Baseline
Planning | Scope | Create WBS | Outputs | Project Documents Updates
Monitoring/Controlling | Scope | Validate Scope | Inputs | Project Mgmt Plan
Monitoring/Controlling | Scope | Validate Scope | Inputs | Requirements Docs
Monitoring/Controlling | Scope | Validate Scope | Inputs | Req. Traceability Matrix
Monitoring/Controlling | Scope | Validate Scope | Inputs | Verified Deliverables
Monitoring/Controlling | Scope | Validate Scope | Inputs | Work Perf. Data
Monitoring/Controlling | Scope | Validate Scope | Tools/Tech's | Inspection
Monitoring/Controlling | Scope | Validate Scope | Tools/Tech's | Group Decision Making Techniques
Monitoring/Controlling | Scope | Validate Scope | Outputs | Accepted Deliverables
Monitoring/Controlling | Scope | Validate Scope | Outputs | Change Requests
Monitoring/Controlling | Scope | Validate Scope | Outputs | Work Perf. Information
Monitoring/Controlling | Scope | Validate Scope | Outputs | Project Documents Updates
Monitoring/Controlling | Scope | Control Scope | Inputs | Project Mgmt Plan
Monitoring/Controlling | Scope | Control Scope | Inputs | Requirements Docs
Monitoring/Controlling | Scope | Control Scope | Inputs | Req. Traceability Matrix
Monitoring/Controlling | Scope | Control Scope | Inputs | Work Perf. Data
Monitoring/Controlling | Scope | Control Scope | Inputs | Org. Process Assets
Monitoring/Controlling | Scope | Control Scope | Tools/Tech's | Variance Analysis
Monitoring/Controlling | Scope | Control Scope | Outputs | Work Perf. Information
Monitoring/Controlling | Scope | Control Scope | Outputs | Change Requests
Monitoring/Controlling | Scope | Control Scope | Outputs | PM Plan Updates
Monitoring/Controlling | Scope | Control Scope | Outputs | Proj. Doc Updates
Monitoring/Controlling | Scope | Control Scope | Outputs | Org. Process Assets Updates
Planning | Time | Plan Schedule Management | Inputs | Project Mgt Plan
Planning | Time | Plan Schedule Management | Inputs | Project Charter
Planning | Time | Plan Schedule Management | Inputs | Enterprise Environmental factors
Planning | Time | Plan Schedule Management | Inputs | Org. Process Assets
Planning | Time | Plan Schedule Management | Tools/Tech's | Expert Judgement
Planning | Time | Plan Schedule Management | Tools/Tech's | Analytical Techniques
Planning | Time | Plan Schedule Management | Tools/Tech's | Meetings
Planning | Time | Plan Schedule Management | Outputs | Schedule Management Plan
Planning | Time | Define Activities | Inputs | Schedule Management Plan
Planning | Time | Define Activities | Inputs | Scope Baseline
Planning | Time | Define Activities | Inputs | Enterprise Environmental factors
Planning | Time | Define Activities | Inputs | Org. Process Assets
Planning | Time | Define Activities | Tools/Tech's | Decomposition
Planning | Time | Define Activities | Tools/Tech's | Rolling Wave Planning
Planning | Time | Define Activities | Tools/Tech's | Expert Judgement
Planning | Time | Define Activities | Outputs | Activity List
Planning | Time | Define Activities | Outputs | Activity Atributes
Planning | Time | Define Activities | Outputs | Milestone List
Planning | Time | Sequence Activities | Inputs | Schedule Management Plan
Planning | Time | Sequence Activities | Inputs | Activity List
Planning | Time | Sequence Activities | Inputs | Activity Attributes
Planning | Time | Sequence Activities | Inputs | Milestone List
Planning | Time | Sequence Activities | Inputs | Project Scope Statement
Planning | Time | Sequence Activities | Inputs | Enterprise Environmental factors
Planning | Time | Sequence Activities | Inputs | Organizational Process Assets
Planning | Time | Sequence Activities | Tools/Tech's | Precedence Diagramming Method (PDM)
Planning | Time | Sequence Activities | Tools/Tech's | Dependency Determination
Planning | Time | Sequence Activities | Tools/Tech's | Leads and Lags
Planning | Time | Sequence Activities | Outputs | Project Schedule Network Diagrams
Planning | Time | Sequence Activities | Outputs | Project Document Updates
Planning | Time | Estimate Activity Resources | Inputs | Schedule Management Plan
Planning | Time | Estimate Activity Resources | Inputs | Activity List
Planning | Time | Estimate Activity Resources | Inputs | Activity Attributes
Planning | Time | Estimate Activity Resources | Inputs | Resource Calendars
Planning | Time | Estimate Activity Resources | Inputs | Risk Register
Planning | Time | Estimate Activity Resources | Inputs | Activity Cost Estimates
Planning | Time | Estimate Activity Resources | Inputs | Enterprise Environmental factors
Planning | Time | Estimate Activity Resources | Inputs | Organizational Process Assets
Planning | Time | Estimate Activity Resources | Tools/Tech's | Exp. Judgement
Planning | Time | Estimate Activity Resources | Tools/Tech's | Alternative Analysis
Planning | Time | Estimate Activity Resources | Tools/Tech's | Pub’d Estimating Data
Planning | Time | Estimate Activity Resources | Tools/Tech's | Bottom-up Estimating
Planning | Time | Estimate Activity Resources | Tools/Tech's | PM Software
Planning | Time | Estimate Activity Resources | Outputs | Activity Resource Requirements
Planning | Time | Estimate Activity Resources | Outputs | Resource Breakdown Structure
Planning | Time | Estimate Activity Resources | Outputs | Project Document Updates
Planning | Time | Estimate Activity Durations | Inputs | Sked Mgmt Plan
Planning | Time | Estimate Activity Durations | Inputs | Activity List
Planning | Time | Estimate Activity Durations | Inputs | Activity Attributes
Planning | Time | Estimate Activity Durations | Inputs | Activity Resource Requirements
Planning | Time | Estimate Activity Durations | Inputs | Resource Calendars
Planning | Time | Estimate Activity Durations | Inputs | Project Scope Statement
Planning | Time | Estimate Activity Durations | Inputs | Risk Register
Planning | Time | Estimate Activity Durations | Inputs | Resource Breakdown Structure
Planning | Time | Estimate Activity Durations | Inputs | Enterprise Env factors
Planning | Time | Estimate Activity Durations | Inputs | Org. Process Assets
Planning | Time | Estimate Activity Durations | Tools/Tech's | Expert Judgment
Planning | Time | Estimate Activity Durations | Tools/Tech's | Analogous Estimating
Planning | Time | Estimate Activity Durations | Tools/Tech's | Parametric Estimating
Planning | Time | Estimate Activity Durations | Tools/Tech's | Three-point Estimating
Planning | Time | Estimate Activity Durations | Tools/Tech's | Group Decision-making Techniques
Planning | Time | Estimate Activity Durations | Tools/Tech's | Reserve Analysis
Planning | Time | Estimate Activity Durations | Outputs | Activity Duration Estimates
Planning | Time | Estimate Activity Durations | Outputs | Project Document Updates
Planning | Time | Develop Schedule | Inputs | Sked Mgmt Plan
Planning | Time | Develop Schedule | Inputs | Activity List
Planning | Time | Develop Schedule | Inputs | Activity Attributes
Planning | Time | Develop Schedule | Inputs | Proj Schedule Network Diagrams
Planning | Time | Develop Schedule | Inputs | Activity Resource Requirements
Planning | Time | Develop Schedule | Inputs | Resource Calendars
Planning | Time | Develop Schedule | Inputs | Activity Duration Estimates
Planning | Time | Develop Schedule | Inputs | Project Scope Statement
Planning | Time | Develop Schedule | Inputs | Risk Register
Planning | Time | Develop Schedule | Inputs | Proj. Staff Assignments
Planning | Time | Develop Schedule | Inputs | Resource Breakdown Structure
Planning | Time | Develop Schedule | Inputs | Enterprise Environmental factors
Planning | Time | Develop Schedule | Inputs | Org. Process Assets
Planning | Time | Develop Schedule | Tools/Tech's | Schedule Network Analysis
Planning | Time | Develop Schedule | Tools/Tech's | Critical Path Method
Planning | Time | Develop Schedule | Tools/Tech's | Critical Chain Method
Planning | Time | Develop Schedule | Tools/Tech's | Resource Optimization Techniques
Planning | Time | Develop Schedule | Tools/Tech's | Modeling Techniques
Planning | Time | Develop Schedule | Tools/Tech's | Leads and Lags
Planning | Time | Develop Schedule | Tools/Tech's | Schedule Compression
Planning | Time | Develop Schedule | Tools/Tech's | Scheduling Tool
Planning | Time | Develop Schedule | Outputs | Schedule Baseline
Planning | Time | Develop Schedule | Outputs | Proj. Schedule
Planning | Time | Develop Schedule | Outputs | Sked Data
Planning | Time | Develop Schedule | Outputs | Proj. Calendars
Planning | Time | Develop Schedule | Outputs | Proj. Mgmt Plan Updates
Planning | Time | Develop Schedule | Outputs | Proj. Doc Updates
Monitoring/Controlling | Time | Control Schedule | Inputs | PM Plan
Monitoring/Controlling | Time | Control Schedule | Inputs | Project Schedule
Monitoring/Controlling | Time | Control Schedule | Inputs | Work Performance Data
Monitoring/Controlling | Time | Control Schedule | Inputs | Project Calendars
Monitoring/Controlling | Time | Control Schedule | Inputs | Schedule Data
Monitoring/Controlling | Time | Control Schedule | Inputs | Org. Process Assets
Monitoring/Controlling | Time | Control Schedule | Tools/Tech's | Performance Reviews
Monitoring/Controlling | Time | Control Schedule | Tools/Tech's | Project Management Software
Monitoring/Controlling | Time | Control Schedule | Tools/Tech's | Resource Optimization Techniques
Monitoring/Controlling | Time | Control Schedule | Tools/Tech's | Modeling Techniques
Monitoring/Controlling | Time | Control Schedule | Tools/Tech's | Leads and Lags
Monitoring/Controlling | Time | Control Schedule | Tools/Tech's | Schedule Compression
Monitoring/Controlling | Time | Control Schedule | Tools/Tech's | Scheduling Tool
Monitoring/Controlling | Time | Control Schedule | Outputs | Work Performance Information
Monitoring/Controlling | Time | Control Schedule | Outputs | Schedule Forecasts
Monitoring/Controlling | Time | Control Schedule | Outputs | Change Requests
Monitoring/Controlling | Time | Control Schedule | Outputs | PM Plan Updates
Monitoring/Controlling | Time | Control Schedule | Outputs | Proj. Doc Updates
Monitoring/Controlling | Time | Control Schedule | Outputs | Organizational Process Assets Updates
Planning | Cost | Plan Cost Management | Inputs | Project Management Plan
Planning | Cost | Plan Cost Management | Inputs | Project Charter
Planning | Cost | Plan Cost Management | Inputs | Enterprise Environmental Factors
Planning | Cost | Plan Cost Management | Inputs | Organizational Process Assets
Planning | Cost | Plan Cost Management | Tools/Tech's | Expert Judgment
Planning | Cost | Plan Cost Management | Tools/Tech's | Analytical Techniques
Planning | Cost | Plan Cost Management | Tools/Tech's | Meetings
Planning | Cost | Plan Cost Management | Outputs | Cost Management Plan
Planning | Cost | Estimate Costs | Inputs | Cost Mgmt Plan
Planning | Cost | Estimate Costs | Inputs | HR Mgmt Plan
Planning | Cost | Estimate Costs | Inputs | Scope Baseline
Planning | Cost | Estimate Costs | Inputs | Project Schedule
Planning | Cost | Estimate Costs | Inputs | Risk Register
Planning | Cost | Estimate Costs | Inputs | Enterprise Environmental Factors
Planning | Cost | Estimate Costs | Inputs | Organizational Process Assets
Planning | Cost | Estimate Costs | Tools/Tech's | Exp. Judgment
Planning | Cost | Estimate Costs | Tools/Tech's | Analogous
Planning | Cost | Estimate Costs | Tools/Tech's | Parametric
Planning | Cost | Estimate Costs | Tools/Tech's | Bottom-up Estimating
Planning | Cost | Estimate Costs | Tools/Tech's | Three-point Estimating
Planning | Cost | Estimate Costs | Tools/Tech's | Reserve Analysis
Planning | Cost | Estimate Costs | Tools/Tech's | Cost of Quality
Planning | Cost | Estimate Costs | Tools/Tech's | PM Software
Planning | Cost | Estimate Costs | Tools/Tech's | Vendor Bid Analysis
Planning | Cost | Estimate Costs | Tools/Tech's | Group Decision-making Techniques
Planning | Cost | Estimate Costs | Outputs | Activity Cost Estimates
Planning | Cost | Estimate Costs | Outputs | Basis of Estimates
Planning | Cost | Estimate Costs | Outputs | Project Document Updates
Planning | Cost | Determine Budget | Inputs | Cost Management Plan
Planning | Cost | Determine Budget | Inputs | Scope Baseline
Planning | Cost | Determine Budget | Inputs | Activity Cost Estimates
Planning | Cost | Determine Budget | Inputs | Basis of Estimates
Planning | Cost | Determine Budget | Inputs | Project Schedule
Planning | Cost | Determine Budget | Inputs | Resource Calendars
Planning | Cost | Determine Budget | Inputs | Risk Register
Planning | Cost | Determine Budget | Inputs | Agreements
Planning | Cost | Determine Budget | Inputs | Organizational Process Assets
Planning | Cost | Determine Budget | Tools/Tech's | Cost Aggregation
Planning | Cost | Determine Budget | Tools/Tech's | Reserve Analysis
Planning | Cost | Determine Budget | Tools/Tech's | Expert Judgment
Planning | Cost | Determine Budget | Tools/Tech's | Historical Relationships
Planning | Cost | Determine Budget | Tools/Tech's | Funding Limit Reconciliation
Planning | Cost | Determine Budget | Outputs | Cost Baseline
Planning | Cost | Determine Budget | Outputs | Project Funding Requirements
Planning | Cost | Determine Budget | Outputs | Project Documents Updates
Monitoring/Controlling | Cost | Control Costs | Inputs | PM Plan
Monitoring/Controlling | Cost | Control Costs | Inputs | Project Funding Requirements
Monitoring/Controlling | Cost | Control Costs | Inputs | Work Performance Data
Monitoring/Controlling | Cost | Control Costs | Inputs | Organizational Process Assets
Monitoring/Controlling | Cost | Control Costs | Tools/Tech's | Earned Value Management
Monitoring/Controlling | Cost | Control Costs | Tools/Tech's | Forecasting
Monitoring/Controlling | Cost | Control Costs | Tools/Tech's | To-complete Performance Index (TCPI)
Monitoring/Controlling | Cost | Control Costs | Tools/Tech's | Performance Reviews
Monitoring/Controlling | Cost | Control Costs | Tools/Tech's | PM Software
Monitoring/Controlling | Cost | Control Costs | Tools/Tech's | Reserve Analysis
Monitoring/Controlling | Cost | Control Costs | Outputs | Work Performance Information
Monitoring/Controlling | Cost | Control Costs | Outputs | Costs Forecasts
Monitoring/Controlling | Cost | Control Costs | Outputs | Change Requests
Monitoring/Controlling | Cost | Control Costs | Outputs | PM Plan Updates
Monitoring/Controlling | Cost | Control Costs | Outputs | Project Documents Updates
Monitoring/Controlling | Cost | Control Costs | Outputs | Organizational Process Updates
Planning | Quality | Plan Quality Management | Inputs | PM Plan
Planning | Quality | Plan Quality Management | Inputs | Stakeholder Register
Planning | Quality | Plan Quality Management | Inputs | Risk Register
Planning | Quality | Plan Quality Management | Inputs | Requirements Documentation
Planning | Quality | Plan Quality Management | Inputs | Enterprise Environmental Factors
Planning | Quality | Plan Quality Management | Inputs | Organizational Process Assets
Planning | Quality | Plan Quality Management | Tools/Tech's | Cost-Benefit Analysis
Planning | Quality | Plan Quality Management | Tools/Tech's | Cost of Quality
Planning | Quality | Plan Quality Management | Tools/Tech's | Seven Basic Quality Tools
Planning | Quality | Plan Quality Management | Tools/Tech's | Benchmarking
Planning | Quality | Plan Quality Management | Tools/Tech's | Design of Experiments
Planning | Quality | Plan Quality Management | Tools/Tech's | Statistical Sampling
Planning | Quality | Plan Quality Management | Tools/Tech's | Additional Quality Planning Tools
Planning | Quality | Plan Quality Management | Tools/Tech's | Meetings
Planning | Quality | Plan Quality Management | Outputs | Quality Management Plan
Planning | Quality | Plan Quality Management | Outputs | Process Improvement Plan
Planning | Quality | Plan Quality Management | Outputs | Quality Metrics
Planning | Quality | Plan Quality Management | Outputs | Quality Checklists
Planning | Quality | Plan Quality Management | Outputs | Project Documents Updates
Executing | Quality | Perform Quality Assurance | Inputs | Quality Mgmt Plan
Executing | Quality | Perform Quality Assurance | Inputs | Process Improvement Plan
Executing | Quality | Perform Quality Assurance | Inputs | Quality Metrics
Executing | Quality | Perform Quality Assurance | Inputs | Quality Control Measurements
Executing | Quality | Perform Quality Assurance | Inputs | Proj. Docs
Executing | Quality | Perform Quality Assurance | Tools/Tech's | Quality Management and Control Tools
Executing | Quality | Perform Quality Assurance | Tools/Tech's | Quality Audits
Executing | Quality | Perform Quality Assurance | Tools/Tech's | Process Analysis
Executing | Quality | Perform Quality Assurance | Outputs | Change Requests
Executing | Quality | Perform Quality Assurance | Outputs | PM Plan Updates
Executing | Quality | Perform Quality Assurance | Outputs | Project Documents Updates
Executing | Quality | Perform Quality Assurance | Outputs | Org. Process Assets Updates
Monitoring/Controlling | Quality | Control Quality | Inputs | PM Plan
Monitoring/Controlling | Quality | Control Quality | Inputs | Quality Metrics
Monitoring/Controlling | Quality | Control Quality | Inputs | Quality Checklists
Monitoring/Controlling | Quality | Control Quality | Inputs | Work Performance Data
Monitoring/Controlling | Quality | Control Quality | Inputs | Approved Change Requests
Monitoring/Controlling | Quality | Control Quality | Inputs | Deliverables
Monitoring/Controlling | Quality | Control Quality | Inputs | Project Documents
Monitoring/Controlling | Quality | Control Quality | Inputs | Organization Process Assets
Monitoring/Controlling | Quality | Control Quality | Tools/Tech's | Seven Basic Quality Tools
Monitoring/Controlling | Quality | Control Quality | Tools/Tech's | Statistical Sampling
Monitoring/Controlling | Quality | Control Quality | Tools/Tech's | Inspection
Monitoring/Controlling | Quality | Control Quality | Tools/Tech's | Approved Change Requests Review
Monitoring/Controlling | Quality | Control Quality | Outputs | Quality Control Measurements
Monitoring/Controlling | Quality | Control Quality | Outputs | Validated Changes
Monitoring/Controlling | Quality | Control Quality | Outputs | Verified Deliverables
Monitoring/Controlling | Quality | Control Quality | Outputs | Work Performance Information
Monitoring/Controlling | Quality | Control Quality | Outputs | Change Requests
Monitoring/Controlling | Quality | Control Quality | Outputs | PM Plan Updates
Monitoring/Controlling | Quality | Control Quality | Outputs | Project Documents Updates
Monitoring/Controlling | Quality | Control Quality | Outputs | Org. Process Assets Updates
Planning | HR | Plan Human Resources Management | Inputs | PM Plan
Planning | HR | Plan Human Resources Management | Inputs | Activity Resource Requirements
Planning | HR | Plan Human Resources Management | Inputs | Enterprise Environmental Factors
Planning | HR | Plan Human Resources Management | Inputs | Organization Process Assets
Planning | HR | Plan Human Resources Management | Tools/Tech's | Org. Charts and Position Descriptions
Planning | HR | Plan Human Resources Management | Tools/Tech's | Networking
Planning | HR | Plan Human Resources Management | Tools/Tech's | Org. Theory
Planning | HR | Plan Human Resources Management | Tools/Tech's | Expert Judgment
Planning | HR | Plan Human Resources Management | Tools/Tech's | Meetings
Planning | HR | Plan Human Resources Management | Outputs | Human Resources Management Plan
Executing | HR | Acquire Project Team | Inputs | HR Management Plan
Executing | HR | Acquire Project Team | Inputs | Enterprise Environmental Factors
Executing | HR | Acquire Project Team | Inputs | Organization Process Assets
Executing | HR | Acquire Project Team | Tools/Tech's | Pre-assignment
Executing | HR | Acquire Project Team | Tools/Tech's | Negotiation
Executing | HR | Acquire Project Team | Tools/Tech's | Acquisition
Executing | HR | Acquire Project Team | Tools/Tech's | Virtual Teams
Executing | HR | Acquire Project Team | Tools/Tech's | Multi-criteria Decision Analysis
Executing | HR | Acquire Project Team | Outputs | Project Staff Assignments
Executing | HR | Acquire Project Team | Outputs | Resource Calendars
Executing | HR | Acquire Project Team | Outputs | Project Management Plan Updates
Executing | HR | Develop Project Team | Inputs | HR Management Plan
Executing | HR | Develop Project Team | Inputs | Project Staff Assignments
Executing | HR | Develop Project Team | Inputs | Resource Calendars
Executing | HR | Develop Project Team | Tools/Tech's | Interpersonal Skills
Executing | HR | Develop Project Team | Tools/Tech's | Training
Executing | HR | Develop Project Team | Tools/Tech's | Team-building Activities
Executing | HR | Develop Project Team | Tools/Tech's | Ground Rules
Executing | HR | Develop Project Team | Tools/Tech's | Colocation
Executing | HR | Develop Project Team | Tools/Tech's | Recognition and Rewards
Executing | HR | Develop Project Team | Tools/Tech's | Personnel Assessment Tools
Executing | HR | Develop Project Team | Outputs | Team Performance Assessments
Executing | HR | Develop Project Team | Outputs | Enterprise Environmental Factors Updates
Executing | HR | Manage Project Team | Inputs | HR Management Plan
Executing | HR | Manage Project Team | Inputs | Project Staff Assignments
Executing | HR | Manage Project Team | Inputs | Team Performance Assessments
Executing | HR | Manage Project Team | Inputs | Issue Log
Executing | HR | Manage Project Team | Inputs | Work Performance Reports
Executing | HR | Manage Project Team | Inputs | Organizational Process Assets
Executing | HR | Manage Project Team | Tools/Tech's | Observations and Conversation
Executing | HR | Manage Project Team | Tools/Tech's | Project Performance Appraisals
Executing | HR | Manage Project Team | Tools/Tech's | Conflict Management
Executing | HR | Manage Project Team | Tools/Tech's | Interpersonal Skills
Executing | HR | Manage Project Team | Outputs | Change Requests
Executing | HR | Manage Project Team | Outputs | PM Plan Updates
Executing | HR | Manage Project Team | Outputs | Project Document Updates
Executing | HR | Manage Project Team | Outputs | Enterprise Environmental Factors Updates
Executing | HR | Manage Project Team | Outputs | Organizational Process Assets Updates
Planning | Communications | Plan Communications Management | Inputs | PM Plan
Planning | Communications | Plan Communications Management | Inputs | Stakeholder Register
Planning | Communications | Plan Communications Management | Inputs | Enterprise Environmental Factors
Planning | Communications | Plan Communications Management | Inputs | Organizational Process Assets
Planning | Communications | Plan Communications Management | Tools/Tech's | Comm. Requirements Analysis
Planning | Communications | Plan Communications Management | Tools/Tech's | Comm. Technology
Planning | Communications | Plan Communications Management | Tools/Tech's | Comm. Models
Planning | Communications | Plan Communications Management | Tools/Tech's | Comm. Methods
Planning | Communications | Plan Communications Management | Tools/Tech's | Meetings
Planning | Communications | Plan Communications Management | Outputs | Communications Management Plan
Planning | Communications | Plan Communications Management | Outputs | Project Documents Updates
Executing | Communications | Manage Communications | Inputs | Comm. Mgmt Plan
Executing | Communications | Manage Communications | Inputs | Work Performance Reports
Executing | Communications | Manage Communications | Inputs | Enterprise Environmental Factors
Executing | Communications | Manage Communications | Inputs | Org. Process Assets
Executing | Communications | Manage Communications | Tools/Tech's | Comm. Technology
Executing | Communications | Manage Communications | Tools/Tech's | Comm. Models
Executing | Communications | Manage Communications | Tools/Tech's | Comm. Methods
Executing | Communications | Manage Communications | Tools/Tech's | Info Mgmt Systems
Executing | Communications | Manage Communications | Tools/Tech's | Performance Reporting
Executing | Communications | Manage Communications | Outputs | Project Communications
Executing | Communications | Manage Communications | Outputs | PM Plan Updates
Executing | Communications | Manage Communications | Outputs | Project Documents Updates
Executing | Communications | Manage Communications | Outputs | Org. Process Assets Updates
Monitoring/Controlling | Communications | Control Communications | Inputs | PM Plan
Monitoring/Controlling | Communications | Control Communications | Inputs | Project Communications
Monitoring/Controlling | Communications | Control Communications | Inputs | Issue Log
Monitoring/Controlling | Communications | Control Communications | Inputs | Work Performance Data
Monitoring/Controlling | Communications | Control Communications | Inputs | Organizational Process Assets
Monitoring/Controlling | Communications | Control Communications | Tools/Tech's | Information Management Systems
Monitoring/Controlling | Communications | Control Communications | Tools/Tech's | Expert Judgment
Monitoring/Controlling | Communications | Control Communications | Tools/Tech's | Meetings
Monitoring/Controlling | Communications | Control Communications | Outputs | Work Performance Information
Monitoring/Controlling | Communications | Control Communications | Outputs | Change Requests
Monitoring/Controlling | Communications | Control Communications | Outputs | PM Plan Updates
Monitoring/Controlling | Communications | Control Communications | Outputs | Project Documents Updates
Monitoring/Controlling | Communications | Control Communications | Outputs | Organizational Process Assets Updates
Planning | Risk | Plan Risk Management | Inputs | PM Plan
Planning | Risk | Plan Risk Management | Inputs | Project Communications
Planning | Risk | Plan Risk Management | Inputs | Project Charter
Planning | Risk | Plan Risk Management | Inputs | Stakeholder Register
Planning | Risk | Plan Risk Management | Inputs | Enterprise Environmental Factors
Planning | Risk | Plan Risk Management | Inputs | Organizational Process Assets
Planning | Risk | Plan Risk Management | Tools/Tech's | Analytical Techniques
Planning | Risk | Plan Risk Management | Tools/Tech's | Expert Judgment
Planning | Risk | Plan Risk Management | Tools/Tech's | Meetings
Planning | Risk | Plan Risk Management | Outputs | Risk Management Plan
Planning | Risk | Identify Risks | Inputs | Risk Mgmt Plan
Planning | Risk | Identify Risks | Inputs | Cost Mgmt Plan
Planning | Risk | Identify Risks | Inputs | Quality Mgmt Plan
Planning | Risk | Identify Risks | Inputs | HR Mgmt Plan
Planning | Risk | Identify Risks | Inputs | Scope Baseline
Planning | Risk | Identify Risks | Inputs | Activity Cost Estimates
Planning | Risk | Identify Risks | Inputs | Activity Duration Estimates
Planning | Risk | Identify Risks | Inputs | Stakeholder Register
Planning | Risk | Identify Risks | Inputs | Project Documents
Planning | Risk | Identify Risks | Inputs | Procurement Documents
Planning | Risk | Identify Risks | Inputs | Enterprise Environmental Factors
Planning | Risk | Identify Risks | Inputs | Organizational Process Assets
Planning | Risk | Identify Risks | Tools/Tech's | Documentation Reviews
Planning | Risk | Identify Risks | Tools/Tech's | Information Gathering Techniques
Planning | Risk | Identify Risks | Tools/Tech's | Checklist Analysis
Planning | Risk | Identify Risks | Tools/Tech's | Assumptions Analysis
Planning | Risk | Identify Risks | Tools/Tech's | Diagramming Techniques
Planning | Risk | Identify Risks | Tools/Tech's | SWOT Analysis
Planning | Risk | Identify Risks | Tools/Tech's | Expert Judgment
Planning | Risk | Identify Risks | Outputs | Risk Register
Planning | Risk | Perform Qualitative Risk Analysis | Inputs | Risk Management Plan
Planning | Risk | Perform Qualitative Risk Analysis | Inputs | Scope Baseline
Planning | Risk | Perform Qualitative Risk Analysis | Inputs | Risk Register
Planning | Risk | Perform Qualitative Risk Analysis | Inputs | Enterprise Environmental Factors
Planning | Risk | Perform Qualitative Risk Analysis | Inputs | Org. Process Assets
Planning | Risk | Perform Qualitative Risk Analysis | Tools/Tech's | Risk Probability and Impact Assessment
Planning | Risk | Perform Qualitative Risk Analysis | Tools/Tech's | Probability and Impact Matrix
Planning | Risk | Perform Qualitative Risk Analysis | Tools/Tech's | Risk Data Quality Assessment
Planning | Risk | Perform Qualitative Risk Analysis | Tools/Tech's | Risk Categorization
Planning | Risk | Perform Qualitative Risk Analysis | Tools/Tech's | Risk Urgency Assessment
Planning | Risk | Perform Qualitative Risk Analysis | Tools/Tech's | Expert Judgment
Planning | Risk | Perform Qualitative Risk Analysis | Outputs | Project Documents Updates
Planning | Risk | Perform Quantitative Analysis | Inputs | Risk Mgmt Plan
Planning | Risk | Perform Quantitative Analysis | Inputs | Cost Mgmt Plan
Planning | Risk | Perform Quantitative Analysis | Inputs | Schedule Mgmt Plan
Planning | Risk | Perform Quantitative Analysis | Inputs | Risk Register
Planning | Risk | Perform Quantitative Analysis | Inputs | Ent. Enviro. Factors
Planning | Risk | Perform Quantitative Analysis | Inputs | Org. Process Assets
Planning | Risk | Perform Quantitative Analysis | Tools/Tech's | Data Gathering and Representation Techniques
Planning | Risk | Perform Quantitative Analysis | Tools/Tech's | Quantitative Risk Analysis and Modeling Techniques
Planning | Risk | Perform Quantitative Analysis | Tools/Tech's | Expert Judgment
Planning | Risk | Perform Quantitative Analysis | Outputs | Project Documents Updates
Planning | Risk | Plan Risk Responses | Inputs | Risk Management Plan
Planning | Risk | Plan Risk Responses | Inputs | Risk Register
Planning | Risk | Plan Risk Responses | Tools/Tech's | Strategies for Negative Risks or Threats
Planning | Risk | Plan Risk Responses | Tools/Tech's | Stategies for Positive Risks or Opportunities
Planning | Risk | Plan Risk Responses | Tools/Tech's | Contingent Response Strategies
Planning | Risk | Plan Risk Responses | Tools/Tech's | Expert Judgment
Planning | Risk | Plan Risk Responses | Outputs | PM Plan Updates
Planning | Risk | Plan Risk Responses | Outputs | Project Documents Updates
Monitoring/Controlling | Risk | Control Risks | Inputs | PM Plan
Monitoring/Controlling | Risk | Control Risks | Inputs | Risk Register
Monitoring/Controlling | Risk | Control Risks | Inputs | Work Performance Data
Monitoring/Controlling | Risk | Control Risks | Inputs | Work Performance Reports
Monitoring/Controlling | Risk | Control Risks | Tools/Tech's | Risk Reassessment
Monitoring/Controlling | Risk | Control Risks | Tools/Tech's | Risk Audits
Monitoring/Controlling | Risk | Control Risks | Tools/Tech's | Variance and Trend Analysis
Monitoring/Controlling | Risk | Control Risks | Tools/Tech's | Technical Performance Measurement
Monitoring/Controlling | Risk | Control Risks | Tools/Tech's | Reserve Analysis
Monitoring/Controlling | Risk | Control Risks | Tools/Tech's | Meetings
Monitoring/Controlling | Risk | Control Risks | Outputs | Work Performance Information
Monitoring/Controlling | Risk | Control Risks | Outputs | Changes Requests
Monitoring/Controlling | Risk | Control Risks | Outputs | PM Plan Updates
Monitoring/Controlling | Risk | Control Risks | Outputs | Project Document Updates
Monitoring/Controlling | Risk | Control Risks | Outputs | Organizational Process Assets Updates
Planning | Procurement | Plan Procurement Management | Inputs | PM Plan
Planning | Procurement | Plan Procurement Management | Inputs | Requirements Documentation
Planning | Procurement | Plan Procurement Management | Inputs | Risk Register
Planning | Procurement | Plan Procurement Management | Inputs | Activity Resource Requirements
Planning | Procurement | Plan Procurement Management | Inputs | Project Schedule
Planning | Procurement | Plan Procurement Management | Inputs | Activity Cost Estimates
Planning | Procurement | Plan Procurement Management | Inputs | Stakeholder Register
Planning | Procurement | Plan Procurement Management | Inputs | Enterprise Environmental Factors
Planning | Procurement | Plan Procurement Management | Inputs | Organizational Process Assets
Planning | Procurement | Plan Procurement Management | Tools/Tech's | Make-or-buy Analysis
Planning | Procurement | Plan Procurement Management | Tools/Tech's | Expert Judgment
Planning | Procurement | Plan Procurement Management | Tools/Tech's | Market Research
Planning | Procurement | Plan Procurement Management | Tools/Tech's | Meetings
Planning | Procurement | Plan Procurement Management | Outputs | Procurement Management Plan
Planning | Procurement | Plan Procurement Management | Outputs | Procurement Statement of Work
Planning | Procurement | Plan Procurement Management | Outputs | Procurement Documents
Planning | Procurement | Plan Procurement Management | Outputs | Source Selection Criteria
Planning | Procurement | Plan Procurement Management | Outputs | Make-or-buy decisions
Planning | Procurement | Plan Procurement Management | Outputs | Change Requests
Planning | Procurement | Plan Procurement Management | Outputs | Project Documents Updates
Executing | Procurement | Conduct Procurements | Inputs | Procurement Management Plan
Executing | Procurement | Conduct Procurements | Inputs | Procurement Documents
Executing | Procurement | Conduct Procurements | Inputs | Source Selection Criteria
Executing | Procurement | Conduct Procurements | Inputs | Seller Proposals
Executing | Procurement | Conduct Procurements | Inputs | Project Documents
Executing | Procurement | Conduct Procurements | Inputs | Make-or-buy Decisions
Executing | Procurement | Conduct Procurements | Inputs | Procurement Statement of Work
Executing | Procurement | Conduct Procurements | Inputs | Organizational Process Assets
Executing | Procurement | Conduct Procurements | Tools/Tech's | Bidder Conference
Executing | Procurement | Conduct Procurements | Tools/Tech's | Proposal Evaluation Techniques
Executing | Procurement | Conduct Procurements | Tools/Tech's | Independent Estimates
Executing | Procurement | Conduct Procurements | Tools/Tech's | Expert Judgment
Executing | Procurement | Conduct Procurements | Tools/Tech's | Advertising
Executing | Procurement | Conduct Procurements | Tools/Tech's | Analytical Techniques
Executing | Procurement | Conduct Procurements | Tools/Tech's | Procurement Negotiations
Executing | Procurement | Conduct Procurements | Outputs | Selected Sellers
Executing | Procurement | Conduct Procurements | Outputs | Agreements
Executing | Procurement | Conduct Procurements | Outputs | Resource Calendars
Executing | Procurement | Conduct Procurements | Outputs | Change Requests
Executing | Procurement | Conduct Procurements | Outputs | PM Plan Updates
Executing | Procurement | Conduct Procurements | Outputs | Project Doc. Updates
Monitoring/Controlling | Procurement | Control Procurements | Inputs | PM Plan
Monitoring/Controlling | Procurement | Control Procurements | Inputs | Procurement Documents
Monitoring/Controlling | Procurement | Control Procurements | Inputs | Agreements
Monitoring/Controlling | Procurement | Control Procurements | Inputs | Approved Change Requests
Monitoring/Controlling | Procurement | Control Procurements | Inputs | Work Performance Reports
Monitoring/Controlling | Procurement | Control Procurements | Inputs | Work Performance Data
Monitoring/Controlling | Procurement | Control Procurements | Tools/Tech's | Contract Change Control System
Monitoring/Controlling | Procurement | Control Procurements | Tools/Tech's | Procurement Performance Reviews
Monitoring/Controlling | Procurement | Control Procurements | Tools/Tech's | Inspections and Audits
Monitoring/Controlling | Procurement | Control Procurements | Tools/Tech's | Performance Reporting
Monitoring/Controlling | Procurement | Control Procurements | Tools/Tech's | Payment Systems
Monitoring/Controlling | Procurement | Control Procurements | Tools/Tech's | Claims Administration
Monitoring/Controlling | Procurement | Control Procurements | Tools/Tech's | Records Management System
Monitoring/Controlling | Procurement | Control Procurements | Outputs | Work Performance Info
Monitoring/Controlling | Procurement | Control Procurements | Outputs | Change Requests
Monitoring/Controlling | Procurement | Control Procurements | Outputs | PM Plan Updates
Monitoring/Controlling | Procurement | Control Procurements | Outputs | Proj Doc Updates
Monitoring/Controlling | Procurement | Control Procurements | Outputs | Org Process Assets Updates
Closing | Procurement | Close Procurements | Inputs | PM Plan
Closing | Procurement | Close Procurements | Inputs | Procurement Documents
Closing | Procurement | Close Procurements | Tools/Tech's | Procurement Audits
Closing | Procurement | Close Procurements | Tools/Tech's | Procurement Negotiations
Closing | Procurement | Close Procurements | Tools/Tech's | Records Management System
Closing | Procurement | Close Procurements | Outputs | Closed Procurements
Closing | Procurement | Close Procurements | Outputs | Org Process Assets Updates
Initiating | Stakeholder | Identify Stakeholders | Inputs | Project Charter
Initiating | Stakeholder | Identify Stakeholders | Inputs | Procurement Documents
Initiating | Stakeholder | Identify Stakeholders | Inputs | Enterprise Environmental Factors
Initiating | Stakeholder | Identify Stakeholders | Inputs | Organizational Process Assets
Initiating | Stakeholder | Identify Stakeholders | Tools/Tech's | Stakeholder Analysis
Initiating | Stakeholder | Identify Stakeholders | Tools/Tech's | Expert Judgment
Initiating | Stakeholder | Identify Stakeholders | Tools/Tech's | Meetings
Initiating | Stakeholder | Identify Stakeholders | Outputs | Stakeholder Register
Planning | Stakeholder | Plan Stakeholder Management | Inputs | PM Plan
Planning | Stakeholder | Plan Stakeholder Management | Inputs | Stakeholder Register
Planning | Stakeholder | Plan Stakeholder Management | Inputs | Enterprise Environmental Factors
Planning | Stakeholder | Plan Stakeholder Management | Inputs | Organizational Process Assets
Planning | Stakeholder | Plan Stakeholder Management | Tools/Tech's | Expert Judgment
Planning | Stakeholder | Plan Stakeholder Management | Tools/Tech's | Meetings
Planning | Stakeholder | Plan Stakeholder Management | Tools/Tech's | Analytical Techniques
Planning | Stakeholder | Plan Stakeholder Management | Outputs | Stakeholder Management Plan
Planning | Stakeholder | Plan Stakeholder Management | Outputs | Project Documents Updates
Executing | Stakeholder | Manage Stakeholder Engagement | Inputs | Stakeholder Management Plan
Executing | Stakeholder | Manage Stakeholder Engagement | Inputs | Communication Management Plan
Executing | Stakeholder | Manage Stakeholder Engagement | Inputs | Change Log
Executing | Stakeholder | Manage Stakeholder Engagement | Inputs | Organizational Process Assets
Executing | Stakeholder | Manage Stakeholder Engagement | Tools/Tech's | Communication Methods
Executing | Stakeholder | Manage Stakeholder Engagement | Tools/Tech's | Interpersonal Skills
Executing | Stakeholder | Manage Stakeholder Engagement | Tools/Tech's | Management Skills
Executing | Stakeholder | Manage Stakeholder Engagement | Outputs | Issue Log
Executing | Stakeholder | Manage Stakeholder Engagement | Outputs | Change Requests
Executing | Stakeholder | Manage Stakeholder Engagement | Outputs | PM Plan Updates
Executing | Stakeholder | Manage Stakeholder Engagement | Outputs | Project Documents Updates
Executing | Stakeholder | Manage Stakeholder Engagement | Outputs | Org. Process Assets Updates
Monitoring/Controlling | Stakeholder | Control Stakeholder Engagement | Inputs | PM Plan
Monitoring/Controlling | Stakeholder | Control Stakeholder Engagement | Inputs | Issue Log
Monitoring/Controlling | Stakeholder | Control Stakeholder Engagement | Inputs | Work Performance Data
Monitoring/Controlling | Stakeholder | Control Stakeholder Engagement | Inputs | Project Documents
Monitoring/Controlling | Stakeholder | Control Stakeholder Engagement | Tools/Tech's | Information Management Systems
Monitoring/Controlling | Stakeholder | Control Stakeholder Engagement | Tools/Tech's | Expert Judgment
Monitoring/Controlling | Stakeholder | Control Stakeholder Engagement | Tools/Tech's | Meetings
Monitoring/Controlling | Stakeholder | Control Stakeholder Engagement | Outputs | Work Performance Information
Monitoring/Controlling | Stakeholder | Control Stakeholder Engagement | Outputs | Change Requests
Monitoring/Controlling | Stakeholder | Control Stakeholder Engagement | Outputs | PM Plan Updates
Monitoring/Controlling | Stakeholder | Control Stakeholder Engagement | Outputs | Project Documents Updates
Monitoring/Controlling | Stakeholder | Control Stakeholder Engagement | Outputs | Organizational Process Assets Updates
SOW
Business Case
Agreements
Enterprise Environmental Factors
Organization Process Assets

## GroupedbyAttrib
Knowledge Area | Process Group | Process | Attribute | Value
Initiating | Integration | Develop Project Charter | Inputs | SOW, Business Case, Agreements, Enterprise Environmental Factors, Organization Process Assets
Initiating | Integration | Develop Project Charter | Tools/Tech's | Expert Judgement, Facilitation Techniques
Initiating | Integration | Develop Project Charter | Outputs | Project Charter
Planning | Integration | Develop Project Management Plan | Inputs | Project Charter, Outputs from other processes, Enterprise Environmental Factors, Organization Process Assets
Planning | Integration | Develop Project Management Plan | Tools/Tech's | Expert Judgement, Facilitation Techniques
Planning | Integration | Develop Project Management Plan | Outputs | Project Management Plan
Executing | Integration | Direct and Manage Project | Inputs | Project Mgt Plan, Approved Change Requests, Enterprise Environmental Factors, Organization Process Assets
Executing | Integration | Direct and Manage Project | Tools/Tech's | Expert Judgement, PM Information Systems, Meetings
Executing | Integration | Direct and Manage Project | Outputs | Deliverables, Work Performance Data, Change Requests, PM Plan Updates, Project Doc Updates
Monitoring/Controlling | Integration | Monitor and Control Project Work | Inputs | Project Mgt Plan, Sked Forecasts, Cost Forecasts, Validated Changes, Work Performance Information, Enterprise Environmental Factors, Organization Process Assets
Monitoring/Controlling | Integration | Monitor and Control Project Work | Tools/Tech's | Expert Judgement, PM Information Systems, Meetings
Monitoring/Controlling | Integration | Monitor and Control Project Work | Outputs | Deliverables, Work Performance Data, Change Requests, PM Plan Updates, Project Doc Updates
Monitoring/Controlling | Integration | Perform Integrated Change Control | Inputs | Project Mgt Plan, Work Performance Reports, Change Requests, Enterprise Env. Factors, Org. Process Assets
Monitoring/Controlling | Integration | Perform Integrated Change Control | Tools/Tech's | Expert Judgement, Meetings, Change Control Tools
Monitoring/Controlling | Integration | Perform Integrated Change Control | Outputs | Approved Change Requests, Change Log, PM Plan Updates, Project Doc Updates
Closing | Integration | Close Project | Inputs | Project Mgt Plan, Accepted Deliverables, Org. Process Assets
Closing | Integration | Close Project | Tools/Tech's | Expert Judgement, Analytical Techniques (regression and trend analysis), Meetings
Closing | Integration | Close Project | Outputs | Final Product, Service or Result Transition, Organizational Process Updates
Planning | Scope | Plan Scope Management | Inputs | Project Mgt Plan, Project Charter, Enterprise Environmental factors, Org. Process Assets
Planning | Scope | Plan Scope Management | Tools/Tech's | Expert Judgement, Meetings
Planning | Scope | Plan Scope Management | Outputs | Scope Management Plan, Requirements Management Plan
Planning | Scope | Collect Requirements | Inputs | Scope Mgmt Plan, Requirements Mgmt Plan, Stakeholder Mgmt Plan, Project Charter, Stakeholder Register
Planning | Scope | Collect Requirements | Tools/Tech's | Interviews, Focus Groups, Facilitated Workshops, Group Creativity, Group Decision Making, Questionaires & Surveys, Observations, Prototypes, Benchmarking, Context Diagrams, Document Analysis
Planning | Scope | Collect Requirements | Outputs | Requirements Documentation, Requirements Traceability Matrix
Planning | Scope | Define Scope | Inputs | Scope Management Plan, Project Charter, Requirements Documentation, Org. Process Assets
Planning | Scope | Define Scope | Tools/Tech's | Expert Judgement, Product Analysis, Alternatives Generation, Facilitated Workshops
Planning | Scope | Define Scope | Outputs | Project Scope Statement, Project Documents Updates
Planning | Scope | Create WBS | Inputs | Scope Mgmt Plan, Proj Scope Statement, Requirements Docs, Enterprise Enviro Factors, Org. Process Assets
Planning | Scope | Create WBS | Tools/Tech's | Decomposition, Expert Judgement
Planning | Scope | Create WBS | Outputs | Scope Baseline, Project Documents Updates
Monitoring/Controlling | Scope | Validate Scope | Inputs | Project Mgmt Plan, Requirements Docs, Req. Traceability Matrix, Verified Deliverables, Work Perf. Data
Monitoring/Controlling | Scope | Validate Scope | Tools/Tech's | Inspection, Group Decision Making Techniques
Monitoring/Controlling | Scope | Validate Scope | Outputs | Accepted Deliverables, Change Requests, Work Perf. Information, Project Documents Updates
Monitoring/Controlling | Scope | Control Scope | Inputs | Project Mgmt Plan, Requirements Docs, Req. Traceability Matrix, Work Perf. Data, Org. Process Assets
Monitoring/Controlling | Scope | Control Scope | Tools/Tech's | Variance Analysis
Monitoring/Controlling | Scope | Control Scope | Outputs | Work Perf. Information, Change Requests, PM Plan Updates, Proj. Doc Updates, Org. Process Assets Updates
Planning | Time | Plan Schedule Management | Inputs | Project Mgt Plan, Project Charter, Enterprise Environmental factors, Org. Process Assets
Planning | Time | Plan Schedule Management | Tools/Tech's | Expert Judgement, Analytical Techniques, Meetings
Planning | Time | Plan Schedule Management | Outputs | Schedule Management Plan
Planning | Time | Define Activities | Inputs | Schedule Management Plan, Scope Baseline, Enterprise Environmental factors, Org. Process Assets
Planning | Time | Define Activities | Tools/Tech's | Decomposition, Rolling Wave Planning, Expert Judgement
Planning | Time | Define Activities | Outputs | Activity List, Activity Atributes, Milestone List
Planning | Time | Sequence Activities | Inputs | Schedule Management Plan, Activity List, Activity Attributes, Milestone List, Project Scope Statement, Enterprise Environmental factors, Organizational Process Assets
Planning | Time | Sequence Activities | Tools/Tech's | Precedence Diagramming Method (PDM), Dependency Determination, Leads and Lags
Planning | Time | Sequence Activities | Outputs | Project Schedule Network Diagrams, Project Document Updates
Planning | Time | Estimate Activity Resources | Inputs | Schedule Management Plan, Activity List, Activity Attributes, Resource Calendars, Risk Register, Activity Cost Estimates, Enterprise Environmental factors, Organizational Process Assets
Planning | Time | Estimate Activity Resources | Tools/Tech's | Exp. Judgement, Alternative Analysis, Pub’d Estimating Data, Bottom-up Estimating, PM Software
Planning | Time | Estimate Activity Resources | Outputs | Activity Resource Requirements, Resource Breakdown Structure, Project Document Updates
Planning | Time | Estimate Activity Durations | Inputs | Sked Mgmt Plan, Activity List, Activity Attributes, Activity Resource Requirements, Resource Calendars, Project Scope Statement, Risk Register, Resource Breakdown Structure, Enterprise Env factors, Org. Process Assets
Planning | Time | Estimate Activity Durations | Tools/Tech's | Expert Judgment, Analogous Estimating, Parametric Estimating, Three-point Estimating, Group Decision-making Techniques, Reserve Analysis
Planning | Time | Estimate Activity Durations | Outputs | Activity Duration Estimates, Project Document Updates
Planning | Time | Develop Schedule | Inputs | Sked Mgmt Plan, Activity List, Activity Attributes, Proj Schedule Network Diagrams, Activity Resource Requirements, Resource Calendars, Activity Duration Estimates, Project Scope Statement, Risk Register, Proj. Staff Assignments, Resource Breakdown Structure, Enterprise Environmental factors, Org. Process Assets
Planning | Time | Develop Schedule | Tools/Tech's | Schedule Network Analysis, Critical Path Method, Critical Chain Method, Resource Optimization Techniques, Modeling Techniques, Leads and Lags, Schedule Compression, Scheduling Tool
Planning | Time | Develop Schedule | Outputs | Schedule Baseline, Proj. Schedule, Sked Data, Proj. Calendars, Proj. Mgmt Plan Updates, Proj. Doc Updates
Monitoring/Controlling | Time | Control Schedule | Inputs | PM Plan, Project Schedule, Work Performance Data, Project Calendars, Schedule Data, Org. Process Assets
Monitoring/Controlling | Time | Control Schedule | Tools/Tech's | Performance Reviews, Project Management Software, Resource Optimization Techniques, Modeling Techniques, Leads and Lags, Schedule Compression, Scheduling Tool
Monitoring/Controlling | Time | Control Schedule | Outputs | Work Performance Information, Schedule Forecasts, Change Requests, PM Plan Updates, Proj. Doc Updates, Organizational Process Assets Updates
Planning | Cost | Plan Cost Management | Inputs | Project Management Plan, Project Charter, Enterprise Environmental Factors, Organizational Process Assets
Planning | Cost | Plan Cost Management | Tools/Tech's | Expert Judgment, Analytical Techniques, Meetings
Planning | Cost | Plan Cost Management | Outputs | Cost Management Plan
Planning | Cost | Estimate Costs | Inputs | Cost Mgmt Plan, HR Mgmt Plan, Scope Baseline, Project Schedule, Risk Register, Enterprise Environmental Factors, Organizational Process Assets
Planning | Cost | Estimate Costs | Tools/Tech's | Exp. Judgment, Analogous, Parametric, Bottom-up Estimating, Three-point Estimating, Reserve Analysis, Cost of Quality, PM Software, Vendor Bid Analysis, Group Decision-making Techniques
Planning | Cost | Estimate Costs | Outputs | Activity Cost Estimates, Basis of Estimates, Project Document Updates
Planning | Cost | Determine Budget | Inputs | Cost Management Plan, Scope Baseline, Activity Cost Estimates, Basis of Estimates, Project Schedule, Resource Calendars, Risk Register, Agreements, Organizational Process Assets
Planning | Cost | Determine Budget | Tools/Tech's | Cost Aggregation, Reserve Analysis, Expert Judgment, Historical Relationships, Funding Limit Reconciliation
Planning | Cost | Determine Budget | Outputs | Cost Baseline, Project Funding Requirements, Project Documents Updates
Monitoring/Controlling | Cost | Control Costs | Inputs | PM Plan, Project Funding Requirements, Work Performance Data, Organizational Process Assets
Monitoring/Controlling | Cost | Control Costs | Tools/Tech's | Earned Value Management, Forecasting, To-complete Performance Index (TCPI), Performance Reviews, PM Software, Reserve Analysis
Monitoring/Controlling | Cost | Control Costs | Outputs | Work Performance Information, Costs Forecasts, Change Requests, PM Plan Updates, Project Documents Updates, Organizational Process Updates
Planning | Quality | Plan Quality Management | Inputs | PM Plan, Stakeholder Register, Risk Register, Requirements Documentation, Enterprise Environmental Factors, Organizational Process Assets
Planning | Quality | Plan Quality Management | Tools/Tech's | Cost-Benefit Analysis, Cost of Quality, Seven Basic Quality Tools, Benchmarking, Design of Experiments, Statistical Sampling, Additional Quality Planning Tools, Meetings
Planning | Quality | Plan Quality Management | Outputs | Quality Management Plan, Process Improvement Plan, Quality Metrics, Quality Checklists, Project Documents Updates
Executing | Quality | Perform Quality Assurance | Inputs | Quality Mgmt Plan, Process Improvement Plan, Quality Metrics, Quality Control Measurements, Proj. Docs
Executing | Quality | Perform Quality Assurance | Tools/Tech's | Quality Management and Control Tools, Quality Audits, Process Analysis
Executing | Quality | Perform Quality Assurance | Outputs | Change Requests, PM Plan Updates, Project Documents Updates, Org. Process Assets Updates
Monitoring/Controlling | Quality | Control Quality | Inputs | PM Plan, Quality Metrics, Quality Checklists, Work Performance Data, Approved Change Requests, Deliverables, Project Documents, Organization Process Assets
Monitoring/Controlling | Quality | Control Quality | Tools/Tech's | Seven Basic Quality Tools, Statistical Sampling, Inspection, Approved Change Requests Review
Monitoring/Controlling | Quality | Control Quality | Outputs | Quality Control Measurements, Validated Changes, Verified Deliverables, Work Performance Information, Change Requests, PM Plan Updates, Project Documents Updates, Org. Process Assets Updates
Planning | HR | Plan Human Resources Management | Inputs | PM Plan, Activity Resource Requirements, Enterprise Environmental Factors, Organization Process Assets
Planning | HR | Plan Human Resources Management | Tools/Tech's | Org. Charts and Position Descriptions, Networking, Org. Theory, Expert Judgment, Meetings
Planning | HR | Plan Human Resources Management | Outputs | Human Resources Management Plan
Executing | HR | Acquire Project Team | Inputs | HR Management Plan, Enterprise Environmental Factors, Organization Process Assets
Executing | HR | Acquire Project Team | Tools/Tech's | Pre-assignment, Negotiation, Acquisition, Virtual Teams, Multi-criteria Decision Analysis
Executing | HR | Acquire Project Team | Outputs | Project Staff Assignments, Resource Calendars, Project Management Plan Updates
Executing | HR | Develop Project Team | Inputs | HR Management Plan, Project Staff Assignments, Resource Calendars
Executing | HR | Develop Project Team | Tools/Tech's | Interpersonal Skills, Training, Team-building Activities, Ground Rules, Colocation, Recognition and Rewards, Personnel Assessment Tools
Executing | HR | Develop Project Team | Outputs | Team Performance Assessments, Enterprise Environmental Factors Updates
Executing | HR | Manage Project Team | Inputs | HR Management Plan, Project Staff Assignments, Team Performance Assessments, Issue Log, Work Performance Reports, Organizational Process Assets
Executing | HR | Manage Project Team | Tools/Tech's | Observations and Conversation, Project Performance Appraisals, Conflict Management, Interpersonal Skills,
Executing | HR | Manage Project Team | Outputs | Change Requests, PM Plan Updates, Project Document Updates, Enterprise Environmental Factors Updates, Organizational Process Assets Updates
Planning | Communications | Plan Communications Management | Inputs | PM Plan, Stakeholder Register, Enterprise Environmental Factors, Organizational Process Assets
Planning | Communications | Plan Communications Management | Tools/Tech's | Comm. Requirements Analysis, Comm. Technology, Comm. Models, Comm. Methods, Meetings
Planning | Communications | Plan Communications Management | Outputs | Communications Management Plan, Project Documents Updates
Executing | Communications | Manage Communications | Inputs | Comm. Mgmt Plan, Work Performance Reports, Enterprise Environmental Factors, Org. Process Assets
Executing | Communications | Manage Communications | Tools/Tech's | Comm. Technology, Comm. Models, Comm. Methods, Info Mgmt Systems, Performance Reporting
Executing | Communications | Manage Communications | Outputs | Project Communications, PM Plan Updates, Project Documents Updates, Org. Process Assets Updates
Monitoring/Controlling | Communications | Control Communications | Inputs | PM Plan, Project Communications, Issue Log, Work Performance Data, Organizational Process Assets
Monitoring/Controlling | Communications | Control Communications | Tools/Tech's | Information Management Systems, Expert Judgment, Meetings
Monitoring/Controlling | Communications | Control Communications | Outputs | Work Performance Information, Change Requests, PM Plan Updates, Project Documents Updates, Organizational Process Assets Updates
Planning | Risk | Plan Risk Management | Inputs | PM Plan, Project Communications, Project Charter, Stakeholder Register, Enterprise Environmental Factors, Organizational Process Assets
Planning | Risk | Plan Risk Management | Tools/Tech's | Analytical Techniques, Expert Judgment, Meetings
Planning | Risk | Plan Risk Management | Outputs | Risk Management Plan
Planning | Risk | Identify Risks | Inputs | Risk Mgmt Plan, Cost Mgmt Plan, Quality Mgmt Plan, HR Mgmt Plan, Scope Baseline, Activity Cost Estimates, Activity Duration Estimates, Stakeholder Register, Project Documents, Procurement Documents, Enterprise Environmental Factors, Organizational Process Assets
Planning | Risk | Identify Risks | Tools/Tech's | Documentation Reviews, Information Gathering Techniques, Checklist Analysis, Assumptions Analysis, Diagramming Techniques, SWOT Analysis, Expert Judgment
Planning | Risk | Identify Risks | Outputs | Risk Register
Planning | Risk | Perform Qualitative Risk Analysis | Inputs | Risk Management Plan, Scope Baseline, Risk Register, Enterprise Environmental Factors, Org. Process Assets
Planning | Risk | Perform Qualitative Risk Analysis | Tools/Tech's | Risk Probability and Impact Assessment, Probability and Impact Matrix, Risk Data Quality Assessment, Risk Categorization, Risk Urgency Assessment, Expert Judgment
Planning | Risk | Perform Qualitative Risk Analysis | Outputs | Project Documents Updates
Planning | Risk | Perform Quantitative Analysis | Inputs | Risk Mgmt Plan, Cost Mgmt Plan, Schedule Mgmt Plan, Risk Register, Ent. Enviro. Factors, Org. Process Assets
Planning | Risk | Perform Quantitative Analysis | Tools/Tech's | Data Gathering and Representation Techniques, Quantitative Risk Analysis and Modeling Techniques, Expert Judgment
Planning | Risk | Perform Quantitative Analysis | Outputs | Project Documents Updates
Planning | Risk | Plan Risk Responses | Inputs | Risk Management Plan, Risk Register
Planning | Risk | Plan Risk Responses | Tools/Tech's | Strategies for Negative Risks or Threats, Stategies for Positive Risks or Opportunities, Contingent Response Strategies, Expert Judgment
Planning | Risk | Plan Risk Responses | Outputs | PM Plan Updates, Project Documents Updates
Monitoring/Controlling | Risk | Control Risks | Inputs | PM Plan, Risk Register, Work Performance Data, Work Performance Reports
Monitoring/Controlling | Risk | Control Risks | Tools/Tech's | Risk Reassessment, Risk Audits, Variance and Trend Analysis, Technical Performance Measurement, Reserve Analysis, Meetings
Monitoring/Controlling | Risk | Control Risks | Outputs | Work Performance Information, Changes Requests, PM Plan Updates, Project Document Updates, Organizational Process Assets Updates
Planning | Procurement | Plan Procurement Management | Inputs | PM Plan, Requirements Documentation, Risk Register, Activity Resource Requirements, Project Schedule, Activity Cost Estimates, Stakeholder Register, Enterprise Environmental Factors, Organizational Process Assets
Planning | Procurement | Plan Procurement Management | Tools/Tech's | Make-or-buy Analysis, Expert Judgment, Market Research, Meetings
Planning | Procurement | Plan Procurement Management | Outputs | Procurement Management Plan, Procurement Statement of Work, Procurement Documents, Source Selection Criteria, Make-or-buy decisions, Change Requests, Project Documents Updates
Executing | Procurement | Conduct Procurements | Inputs | Procurement Management Plan, Procurement Documents, Source Selection Criteria, Seller Proposals, Project Documents, Make-or-buy Decisions, Procurement Statement of Work, Organizational Process Assets
Executing | Procurement | Conduct Procurements | Tools/Tech's | Bidder Conference, Proposal Evaluation Techniques, Independent Estimates, Expert Judgment, Advertising, Analytical Techniques, Procurement Negotiations
Executing | Procurement | Conduct Procurements | Outputs | Selected Sellers, Agreements, Resource Calendars, Change Requests, PM Plan Updates, Project Doc. Updates
Monitoring/Controlling | Procurement | Control Procurements | Inputs | PM Plan, Procurement Documents, Agreements, Approved Change Requests, Work Performance Reports, Work Performance Data
Monitoring/Controlling | Procurement | Control Procurements | Tools/Tech's | Contract Change Control System, Procurement Performance Reviews, Inspections and Audits, Performance Reporting, Payment Systems, Claims Administration, Records Management System
Monitoring/Controlling | Procurement | Control Procurements | Outputs | Work Performance Info, Change Requests, PM Plan Updates, Proj Doc Updates, Org Process Assets Updates
Closing | Procurement | Close Procurements | Inputs | PM Plan, Procurement Documents
Closing | Procurement | Close Procurements | Tools/Tech's | Procurement Audits, Procurement Negotiations, Records Management System
Closing | Procurement | Close Procurements | Outputs | Closed Procurements, Org Process Assets Updates
Initiating | Stakeholder | Identify Stakeholders | Inputs | Project Charter, Procurement Documents, Enterprise Environmental Factors, Organizational Process Assets
Initiating | Stakeholder | Identify Stakeholders | Tools/Tech's | Stakeholder Analysis, Expert Judgment, Meetings
Initiating | Stakeholder | Identify Stakeholders | Outputs | Stakeholder Register
Planning | Stakeholder | Plan Stakeholder Management | Inputs | PM Plan, Stakeholder Register, Enterprise Environmental Factors, Organizational Process Assets
Planning | Stakeholder | Plan Stakeholder Management | Tools/Tech's | Expert Judgment, Meetings, Analytical Techniques
Planning | Stakeholder | Plan Stakeholder Management | Outputs | Stakeholder Management Plan, Project Documents Updates
Executing | Stakeholder | Manage Stakeholder Engagement | Inputs | Stakeholder Management Plan, Communication Management Plan, Change Log, Organizational Process Assets
Executing | Stakeholder | Manage Stakeholder Engagement | Tools/Tech's | Communication Methods, Interpersonal Skills, Management Skills
Executing | Stakeholder | Manage Stakeholder Engagement | Outputs | Issue Log, Change Requests, PM Plan Updates, Project Documents Updates, Org. Process Assets Updates
Monitoring/Controlling | Stakeholder | Control Stakeholder Engagement | Inputs | PM Plan, Issue Log, Work Performance Data, Project Documents
Monitoring/Controlling | Stakeholder | Control Stakeholder Engagement | Tools/Tech's | Information Management Systems, Expert Judgment, Meetings
Monitoring/Controlling | Stakeholder | Control Stakeholder Engagement | Outputs | Work Performance Information, Change Requests, PM Plan Updates, Project Documents Updates, Organizational Process Assets Updates

## ProcessList
Process | Process Group | Knowledge Area
Develop Project Charter | Integration | Initiating
Develop Project Management Plan | Integration | Planning
Direct and Manage Project | Integration | Executing
Monitor and Control Project Work | Integration | Monitoring/Controlling
Perform Integrated Change Control | Integration | Monitoring/Controlling
Close Project | Integration | Closing
Plan Scope Management | Scope | Planning
Collect Requirements | Scope | Planning
Define Scope | Scope | Planning
Create WBS | Scope | Planning
Validate Scope | Scope | Monitoring/Controlling
Control Scope | Scope | Monitoring/Controlling
Plan Schedule Management | Time | Planning
Define Activities | Time | Planning
Sequence Activities | Time | Planning
Estimate Activity Resources | Time | Planning
Estimate Activity Durations | Time | Planning
Develop Schedule | Time | Planning
Control Schedule | Time | Monitoring/Controlling
Plan Cost Management | Cost | Planning
Estimate Costs | Cost | Planning
Determine Budget | Cost | Planning
Control Costs | Cost | Monitoring/Controlling
Plan Quality Management | Quality | Planning
Perform Quality Assurance | Quality | Executing
Control Quality | Quality | Monitoring/Controlling
Plan Human Resources Management | HR | Planning
Acquire Project Team | HR | Executing
Develop Project Team | HR | Executing
Manage Project Team | HR | Executing
Plan Communications Management | Communications | Planning
Manage Communications | Communications | Executing
Control Communications | Communications | Monitoring/Controlling
Plan Risk Management | Risk | Planning
Identify Risks | Risk | Planning
Perform Qualitative Risk Analysis | Risk | Planning
Perform Quantitative Analysis | Risk | Planning
Plan Risk Responses | Risk | Planning
Control Risks | Risk | Monitoring/Controlling
Plan Procurement Management | Procurement | Planning
Conduct Procurements | Procurement | Executing
Control Procurements | Procurement | Monitoring/Controlling
Close Procurements | Procurement | Closing
Identify Stakeholders | Stakeholder | Initiating
Plan Stakeholder Management | Stakeholder | Planning
Manage Stakeholder Engagement | Stakeholder | Executing
Control Stakeholder Engagement | Stakeholder | Monitoring/Controlling

## Text
Develop Project Charter
Inputs: SOW, Business Case, Agreements, Enterprise Environmental Factors, Organization Process Assets
Tools/Techniques: Expert Judgement, Facilitation Techniques
Outputs: Project Charter
Develop Project Management Plan
Inputs: Project Charter, Outputs from other processes, Enterprise Environmental Factors, Organization Process Assets
Tools/Techniques: Expert Judgement, Facilitation Techniques
Outputs: Project Management Plan
Direct and Manage Project
Inputs: Project Mgt Plan, Approved Change Requests, Enterprise Environmental Factors, Organization Process Assets
Tools/Techniques: Expert Judgement, PM Information Systems, Meetings
Outputs: Deliverables, Work Performance Data, Change Requests, PM Plan Updates, Project Doc Updates
Monitor and Control Project Work
Inputs: Project Mgt Plan, Sked Forecasts, Cost Forecasts, Validated Changes, Work Performance Information, Enterprise Environmental Factors, Organization Process Assets
Tools/Techniques: Expert Judgement, PM Information Systems, Meetings
Outputs: Deliverables, Work Performance Data, Change Requests, PM Plan Updates, Project Doc Updates
Perform Integrated Change Control
Inputs: Project Mgt Plan, Work Performance Reports, Change Requests, Enterprise Env. Factors, Org. Process Assets
Tools/Techniques: Expert Judgement, Meetings, Change Control Tools
Outputs: Approved Change Requests, Change Log, PM Plan Updates, Project Doc Updates
Close Project
Inputs: Project Mgt Plan, Accepted Deliverables, Org. Process Assets
Tools/Techniques: Expert Judgement, Analytical Techniques (regression and trend analysis), Meetings
Outputs: Final Product, Service or Result Transition, Organizational Process Updates
Plan Scope Management
Inputs: Project Mgt Plan, Project Charter, Enterprise Environmental factors, Org. Process Assets
Tools/Techniques: Expert Judgement, Meetings
Outputs: Scope Management Plan, Requirements Management Plan
Collect Requirements
Inputs: Scope Mgmt Plan, Requirements Mgmt Plan, Stakeholder Mgmt Plan, Project Charter, Stakeholder Register
Tools/Techniques: Interviews, Focus Groups, Facilitated Workshops, Group Creativity, Group Decision Making, Questionaires & Surveys, Observations, Prototypes, Benchmarking, Context Diagrams, Document Analysis
Outputs: Requirements Documentation, Requirements Traceability Matrix
Define Scope
Inputs: Scope Management Plan, Project Charter, Requirements Documentation, Org. Process Assets
Tools/Techniques: Expert Judgement, Product Analysis, Alternatives Generation, Facilitated Workshops
Outputs: Project Scope Statement, Project Documents Updates
Create WBS
Inputs: Scope Mgmt Plan, Proj Scope Statement, Requirements Docs, Enterprise Enviro Factors, Org. Process Assets
Tools/Techniques: Decomposition, Expert Judgement
Outputs: Scope Baseline, Project Documents Updates
Validate Scope
Inputs: Project Mgmt Plan, Requirements Docs, Req. Traceability Matrix, Verified Deliverables, Work Perf. Data
Tools/Techniques: Inspection, Group Decision Making Techniques
Outputs: Accepted Deliverables, Change Requests, Work Perf. Information, Project Documents Updates
Control Scope
Inputs: Project Mgmt Plan, Requirements Docs, Req. Traceability Matrix, Work Perf. Data, Org. Process Assets
Tools/Techniques: Variance Analysis
Outputs: Work Perf. Information, Change Requests, PM Plan Updates, Proj. Doc Updates, Org. Process Assets Updates
Plan Schedule Management
Inputs: Project Mgt Plan, Project Charter, Enterprise Environmental factors, Org. Process Assets
Tools/Techniques: Expert Judgement, Analytical Techniques, Meetings
Outputs: Schedule Management Plan
Define Activities
Inputs: Schedule Management Plan, Scope Baseline, Enterprise Environmental factors, Org. Process Assets
Tools/Techniques: Decomposition, Rolling Wave Planning, Expert Judgement
Outputs: Activity List, Activity Atributes, Milestone List
Sequence Activities
Inputs: Schedule Management Plan, Activity List, Activity Attributes, Milestone List, Project Scope Statement, Enterprise Environmental factors, Organizational Process Assets
Tools/Techniques: Precedence Diagramming Method (PDM), Dependency Determination, Leads and Lags
Outputs: Project Schedule Network Diagrams, Project Document Updates
Estimate Activity Resources
Inputs: Schedule Management Plan, Activity List, Activity Attributes, Resource Calendars, Risk Register, Activity Cost Estimates, Enterprise Environmental factors, Organizational Process Assets
Tools/Techniques: Exp. Judgement, Alternative Analysis, Pub’d Estimating Data, Bottom-up Estimating, PM Software
Outputs: Activity Resource Requirements, Resource Breakdown Structure, Project Document Updates
Estimate Activity Durations
Inputs: Sked Mgmt Plan, Activity List, Activity Attributes, Activity Resource Requirements, Resource Calendars, Project Scope Statement, Risk Register, Resource Breakdown Structure, Enterprise Env factors, Org. Process Assets
Tools/Techniques: Expert Judgment, Analogous Estimating, Parametric Estimating, Three-point Estimating, Group Decision-making Techniques, Reserve Analysis
Outputs: Activity Duration Estimates, Project Document Updates
Develop Schedule
Inputs: Sked Mgmt Plan, Activity List, Activity Attributes, Proj Schedule Network Diagrams, Activity Resource Requirements, Resource Calendars, Activity Duration Estimates, Project Scope Statement, Risk Register, Proj. Staff Assignments, Resource Breakdown Structure, Enterprise Environmental factors, Org. Process Assets
Tools/Techniques: Schedule Network Analysis, Critical Path Method, Critical Chain Method, Resource Optimization Techniques, Modeling Techniques, Leads and Lags, Schedule Compression, Scheduling Tool
Outputs: Schedule Baseline, Proj. Schedule, Sked Data, Proj. Calendars, Proj. Mgmt Plan Updates, Proj. Doc Updates
Control Schedule
Inputs: PM Plan, Project Schedule, Work Performance Data, Project Calendars, Schedule Data, Org. Process Assets
Tools/Techniques: Performance Reviews, Project Management Software, Resource Optimization Techniques, Modeling Techniques, Leads and Lags, Schedule Compression, Scheduling Tool
Outputs: Work Performance Information, Schedule Forecasts, Change Requests, PM Plan Updates, Proj. Doc Updates, Organizational Process Assets Updates
Plan Cost Management
Inputs: Project Management Plan, Project Charter, Enterprise Environmental Factors, Organizational Process Assets
Tools/Techniques: Expert Judgment, Analytical Techniques, Meetings
Outputs: Cost Management Plan
Estimate Costs
Inputs: Cost Mgmt Plan, HR Mgmt Plan, Scope Baseline, Project Schedule, Risk Register, Enterprise Environmental Factors, Organizational Process Assets
Tools/Techniques: Exp. Judgment, Analogous, Parametric, Bottom-up Estimating, Three-point Estimating, Reserve Analysis, Cost of Quality, PM Software, Vendor Bid Analysis, Group Decision-making Techniques
Outputs: Activity Cost Estimates, Basis of Estimates, Project Document Updates
Determine Budget
Inputs: Cost Management Plan, Scope Baseline, Activity Cost Estimates, Basis of Estimates, Project Schedule, Resource Calendars, Risk Register, Agreements, Organizational Process Assets
Tools/Techniques: Cost Aggregation, Reserve Analysis, Expert Judgment, Historical Relationships, Funding Limit Reconciliation
Outputs: Cost Baseline, Project Funding Requirements, Project Documents Updates
Control Costs
Inputs: PM Plan, Project Funding Requirements, Work Performance Data, Organizational Process Assets
Tools/Techniques: Earned Value Management, Forecasting, To-complete Performance Index (TCPI), Performance Reviews, PM Software, Reserve Analysis
Outputs: Work Performance Information, Costs Forecasts, Change Requests, PM Plan Updates, Project Documents Updates, Organizational Process Updates
Plan Quality Management
Inputs: PM Plan, Stakeholder Register, Risk Register, Requirements Documentation, Enterprise Environmental Factors, Organizational Process Assets
Tools/Techniques: Cost-Benefit Analysis, Cost of Quality, Seven Basic Quality Tools, Benchmarking, Design of Experiments, Statistical Sampling, Additional Quality Planning Tools, Meetings
Outputs: Quality Management Plan, Process Improvement Plan, Quality Metrics, Quality Checklists, Project Documents Updates
Perform Quality Assurance
Inputs: Quality Mgmt Plan, Process Improvement Plan, Quality Metrics, Quality Control Measurements, Proj. Docs
Tools/Techniques: Quality Management and Control Tools, Quality Audits, Process Analysis
Outputs: Change Requests, PM Plan Updates, Project Documents Updates, Org. Process Assets Updates
Control Quality
Inputs: PM Plan, Quality Metrics, Quality Checklists, Work Performance Data, Approved Change Requests, Deliverables, Project Documents, Organization Process Assets
Tools/Techniques: Seven Basic Quality Tools, Statistical Sampling, Inspection, Approved Change Requests Review
Outputs: Quality Control Measurements, Validated Changes, Verified Deliverables, Work Performance Information, Change Requests, PM Plan Updates, Project Documents Updates, Org. Process Assets Updates
Plan Human Resources Management
Inputs: PM Plan, Activity Resource Requirements, Enterprise Environmental Factors, Organization Process Assets
Tools/Techniques: Org. Charts and Position Descriptions, Networking, Org. Theory, Expert Judgment, Meetings
Outputs: Human Resources Management Plan
Acquire Project Team
Inputs: HR Management Plan, Enterprise Environmental Factors, Organization Process Assets
Tools/Techniques: Pre-assignment, Negotiation, Acquisition, Virtual Teams, Multi-criteria Decision Analysis
Outputs: Project Staff Assignments, Resource Calendars, Project Management Plan Updates
Develop Project Team
Inputs: HR Management Plan, Project Staff Assignments, Resource Calendars
Tools/Techniques: Interpersonal Skills, Training, Team-building Activities, Ground Rules, Colocation, Recognition and Rewards, Personnel Assessment Tools
Outputs: Team Performance Assessments, Enterprise Environmental Factors Updates
Manage Project Team
Inputs: HR Management Plan, Project Staff Assignments, Team Performance Assessments, Issue Log, Work Performance Reports, Organizational Process Assets
Tools/Techniques: Observations and Conversation, Project Performance Appraisals, Conflict Management, Interpersonal Skills,
Outputs: Change Requests, PM Plan Updates, Project Document Updates, Enterprise Environmental Factors Updates, Organizational Process Assets Updates
Plan Communications Management
Inputs: PM Plan, Stakeholder Register, Enterprise Environmental Factors, Organizational Process Assets
Tools/Techniques: Comm. Requirements Analysis, Comm. Technology, Comm. Models, Comm. Methods, Meetings
Outputs: Communications Management Plan, Project Documents Updates
Manage Communications
Inputs: Comm. Mgmt Plan, Work Performance Reports, Enterprise Environmental Factors, Org. Process Assets
Tools/Techniques: Comm. Technology, Comm. Models, Comm. Methods, Info Mgmt Systems, Performance Reporting
Outputs: Project Communications, PM Plan Updates, Project Documents Updates, Org. Process Assets Updates
Control Communications
Inputs: PM Plan, Project Communications, Issue Log, Work Performance Data, Organizational Process Assets
Tools/Techniques: Information Management Systems, Expert Judgment, Meetings
Outputs: Work Performance Information, Change Requests, PM Plan Updates, Project Documents Updates, Organizational Process Assets Updates
Plan Risk Management
Inputs: PM Plan, Project Communications, Project Charter, Stakeholder Register, Enterprise Environmental Factors, Organizational Process Assets
Tools/Techniques: Analytical Techniques, Expert Judgment, Meetings
Outputs: Risk Management Plan
Identify Risks
Inputs: Risk Mgmt Plan, Cost Mgmt Plan, Quality Mgmt Plan, HR Mgmt Plan, Scope Baseline, Activity Cost Estimates, Activity Duration Estimates, Stakeholder Register, Project Documents, Procurement Documents, Enterprise Environmental Factors, Organizational Process Assets
Tools/Techniques: Documentation Reviews, Information Gathering Techniques, Checklist Analysis, Assumptions Analysis, Diagramming Techniques, SWOT Analysis, Expert Judgment
Outputs: Risk Register
Perform Qualitative Risk Analysis
Inputs: Risk Management Plan, Scope Baseline, Risk Register, Enterprise Environmental Factors, Org. Process Assets
Tools/Techniques: Risk Probability and Impact Assessment, Probability and Impact Matrix, Risk Data Quality Assessment, Risk Categorization, Risk Urgency Assessment, Expert Judgment
Outputs: Project Documents Updates
Perform Quantitative Analysis
Inputs: Risk Mgmt Plan, Cost Mgmt Plan, Schedule Mgmt Plan, Risk Register, Ent. Enviro. Factors, Org. Process Assets
Tools/Techniques: Data Gathering and Representation Techniques, Quantitative Risk Analysis and Modeling Techniques, Expert Judgment
Outputs: Project Documents Updates
Plan Risk Responses
Inputs: Risk Management Plan, Risk Register
Tools/Techniques: Strategies for Negative Risks or Threats, Stategies for Positive Risks or Opportunities, Contingent Response Strategies, Expert Judgment
Outputs: PM Plan Updates, Project Documents Updates
Control Risks
Inputs: PM Plan, Risk Register, Work Performance Data, Work Performance Reports
Tools/Techniques: Risk Reassessment, Risk Audits, Variance and Trend Analysis, Technical Performance Measurement, Reserve Analysis, Meetings
Outputs: Work Performance Information, Changes Requests, PM Plan Updates, Project Document Updates, Organizational Process Assets Updates
Plan Procurement Management
Inputs: PM Plan, Requirements Documentation, Risk Register, Activity Resource Requirements, Project Schedule, Activity Cost Estimates, Stakeholder Register, Enterprise Environmental Factors, Organizational Process Assets
Tools/Techniques: Make-or-buy Analysis, Expert Judgment, Market Research, Meetings
Outputs: Procurement Management Plan, Procurement Statement of Work, Procurement Documents, Source Selection Criteria, Make-or-buy decisions, Change Requests, Project Documents Updates
Conduct Procurements
Inputs: Procurement Management Plan, Procurement Documents, Source Selection Criteria, Seller Proposals, Project Documents, Make-or-buy Decisions, Procurement Statement of Work, Organizational Process Assets
Tools/Techniques: Bidder Conference, Proposal Evaluation Techniques, Independent Estimates, Expert Judgment, Advertising, Analytical Techniques, Procurement Negotiations
Outputs: Selected Sellers, Agreements, Resource Calendars, Change Requests, PM Plan Updates, Project Doc. Updates
Control Procurements
Inputs: PM Plan, Procurement Documents, Agreements, Approved Change Requests, Work Performance Reports, Work Performance Data
Tools/Techniques: Contract Change Control System, Procurement Performance Reviews, Inspections and Audits, Performance Reporting, Payment Systems, Claims Administration, Records Management System
Outputs: Work Performance Info, Change Requests, PM Plan Updates, Proj Doc Updates, Org Process Assets Updates
Close Procurements
Inputs: PM Plan, Procurement Documents
Tools/Techniques: Procurement Audits, Procurement Negotiations, Records Management System
Outputs: Closed Procurements, Org Process Assets Updates
Identify Stakeholders
Inputs: Project Charter, Procurement Documents, Enterprise Environmental Factors, Organizational Process Assets
Tools/Techniques: Stakeholder Analysis, Expert Judgment, Meetings
Outputs: Stakeholder Register
Plan Stakeholder Management
Inputs: PM Plan, Stakeholder Register, Enterprise Environmental Factors, Organizational Process Assets
Tools/Techniques: Expert Judgment, Meetings, Analytical Techniques
Outputs: Stakeholder Management Plan, Project Documents Updates
Manage Stakeholder Engagement
Inputs: Stakeholder Management Plan, Communication Management Plan, Change Log, Organizational Process Assets
Tools/Techniques: Communication Methods, Interpersonal Skills, Management Skills
Outputs: Issue Log, Change Requests, PM Plan Updates, Project Documents Updates, Org. Process Assets Updates
Control Stakeholder Engagement
Inputs: PM Plan, Issue Log, Work Performance Data, Project Documents
Tools/Techniques: Information Management Systems, Expert Judgment, Meetings
Outputs: Work Performance Information, Change Requests, PM Plan Updates, Project Documents Updates, Organizational Process Assets Updates